## Sheet1
ONLINE SUPER MARKET
SKILLS REQUIRED:JAVA,HTML,CSS,JAVASCRIPT,MYSQL,PHP |  |  |  | TEAM MEMBER
MIRTUNJAY KUMAR(16BCE1179)
MODULE NO | MODULE NAME | SUB-TASK | TASK DETAILS | LOC | DURATION(IN DAYS) | TYPE OF SOFTWARE | HUMAN EFFORT | RESOURCE COST | TRAINNING COST | SOFTWARE COST | TOTAL DURATION
1 | administrative | MANAGING | managing database update,delete,insertion,display of product and information | 200 | 42946 | 2017-09-20 | 1 | RS:200 | RS:600 | NULL | 50
|  | Providing security | secure transaction fascilities for customer | 300 | 2017-08-01 | 2017-08-29 | 2 |  |  |  | 29
|  | user profile | managing and updating user profile details | 150 | 2017-08-03 | 2017-08-24 | 1 | ELECTRICITY | NPTEL VIDEOS |  | 21
|  | transaction | controlling transaction fascilities | 150 | 2017-08-15 | 2017-09-26 | 1 | INTERNET USAGE |  |  | 41
|  | consistency | providing data integrity and consistency | 200 | 2017-08-06 | 2017-08-27 | 2 |  |  |  | 21
2 |  | SEARCH OPTION | displaying atleast 10 matching product on search | 150 | 2017-08-18 | 2017-08-29 | 1 | RS:200 | RS:100 | NULL | 11
|  | browsing with caaregories | providing client fascilities to browse product in categories wise classification | 100 | 2017-08-10 | 2017-09-21 | 2 | ELECTRICITY |  |  | 11
| PURCHASE | deatiled product view | provide customer details of product | 100 | 2017-08-10 | 2017-08-29 | 1 | INTERNET | NPTEL VIDEOS |  | 19
|  | option for wishlist and cart | provide customer benifit of adding product to car and wishlist | 150 | 2017-08-12 | 2017-09-24 | 1 | DATABASE DEVELOPMENT |  |  | 12
|  | no of item in cart | display the number of item in the cart | 100 | 2017-08-08 | 2017-08-25 | 2 |  |  |  | 17
3 |  | login and register | display forms for login and register to the user | 300 | 2017-08-30 | 2017-09-13 | 1 | RS:100 | NULL | NULL | 13
| customer and employee | display customer details | display the profile of customer | 200 | 2017-09-02 | 2017-09-09 | 1 |  |  |  | 7
|  | displaypurchase details | display products in cart | 150 | 2017-09-04 | 2017-09-11 | 2 |  |  |  | 7
|  | discount and offer | display discount available for customer and special offer | 160 | 2017-09-05 | 2017-09-19 | 1 |  |  |  | 14
4 |  | configurable product | display all the product tha can be configured | 100 | 2017-09-09 | 2017-09-16 | 1 | NULL | NULL | NULL | 7
| sales | seller details | display manufacturer details and isbn of product and lot no also adress of manufactureer | 100 | 2017-09-09 | 2017-09-16 | 1 |  |  |  | 7
|  | featured product | display the featured product of store | 150 | 2017-09-11 | 2017-09-25 | 2 |  |  |  | 14
|  | discount and offer of the day | display today;'s discounted product and detailed offers | 200 | 2017-09-13 | 2017-09-21 | 2 |  |  |  | 8
|  | rating of product and service | provision for rating product qualities and service | 150 | 2017-09-14 | 2017-09-28 | 1 |  |  |  | 14
5 |  | DISPLAY BILL | DISPLAY BILL OF PRODUCT | 200 | 2017-09-16 | 9/23/201 | 2 | NULL | NULL | NULL | 7
| BILLING | PURCHASED PRODUCT | DISPLAY PURCHASED PRODUCT AND SERVICES | 150 | 2017-09-17 | 2017-09-24 | 2 |  |  |  | 7
|  | ADDRESS | DISPLAY THE ADRESS TO DISPATCH THE PRODUCT | 100 | 2017-09-18 | 2019-09-25 | 1 |  |  |  | 7
|  | TAX | CALCULATE AND ADD TAX TO BILL ACOORDING TO GST | 100 | 2017-09-19 | 2017-09-29 | 1 |  |  |  | 10
6 |  | FEEDBACK SUBMISSION | PROVIDING PROVISION TO FILL FEEDBACK | 100 | 2017-08-21 | 2017-09-23 | 1 | RS:100 | NULL | NULL | 2
| CUSTOMER CARE | FAQ'S | DISPLAYING FAQ'S FOR CUSTOMER HELP | 200 | 2017-08-23 | 2017-09-24 | 2 |  |  |  | 1
|  | STORE INFO | CONTACT INFORMATION FOR FURTHER QUERRIES AND HELP OF CUSTOMER | 150 | 2017-09-25 | 2017-09-29 | 1 | PERSON FOR MONITORING |  |  | 4
|  | SERVICE RATING | PROVIDING FACILITIES FOR RATING SERVICE | 100 | 2017-09-21 | 2017-09-29 | 1 |  |  |  | 8